## Sheet1
Starting Criteria
Week | 7 | Days
Weekly Work | 5 | Days
Weekly Work | 37 | Hours
Prof Dev Module | 0.25 | Proportion of total year effort
Live Project | 0.55 | Proportion of Prof Dev
Effort |  |  |  | Totals |  |  | For Selection |  | For Selection |  | For Selection
Minimum |  |  |  | 5.0875 | Hours per Week |  | Minimum |  | Term |  | Requirements
Expected | 1 | Extra-curricular hours per night |  | 10.0875 | Hours per Week |  | Expected |  | Non-term |  | Design
Stretch | 2 | Extra curricular hours per night |  | 15.0875 | Hours per Week |  | Stretch |  |  |  | Impl
None
|  | Year | Month | Day
Start Date |  | 2018 | 10 | 29 | 2018-10-29
End Date |  | 2019 | 2 | 25 | 2018-02-25
|  |  | Investigation | [6 empty] | 116.225
|  |  | Requirements |  |  | 0 | Design |  |  | 116.225 | Implementation | [8 empty] | 282.975 | Release |  |  | 141.4
Team | Park Elsewhere
|  |  | Term | Term | Term | Term | Term | Term | Term | Non-term | Non-term | Non-term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term | Term |  | Hours
| Member | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
|  | Sprint | 0.75 |  | 1.75 |  | 2.75 |  | 3.75 |  | 4.75 |  | 5.75 |  | 6.75 |  | 7.75 |  | 8.75 |  | 9.75 |  | 10.75
|  | Commencing | 2018-10-29 | 2018-11-05 | 2018-11-12 | 2018-11-19 | 2018-11-26 | 2018-12-03 | 2018-12-10 | 2018-12-17 | 2018-12-24 | 2018-12-31 | 2019-01-07 | 2019-01-14 | 2019-01-21 | 2019-01-28 | 2019-02-04 | 2019-02-11 | 2019-02-18 | 2019-02-25 | 2019-03-04 | 2019-03-11 | 2019-03-18 | 2019-03-25 |  | Minimum | Expected | Stretch | Total
| cheeriosman2018 |  | None | None | None | None | Expected | Minimum | Minimum | Stretch | None | None | Minimum | Minimum | Minimum | Minimum | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected |  | 30.525 | 90.7875 | 15.0875 | 136.4
| FalseRocket2018 |  | None | None | None | None | Minimum | Minimum | Minimum | None | None | None | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum | Minimum |  | 76.3125 | 0 | 0 | 76.3125
| FruitFibre |  | None | None | None | None | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected |  | 0 | 181.575 | 0 | 181.575
| i6045739 |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| KarenPatel |  | None | None | None | None | Minimum | Expected | Expected | None | None | None | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected | Expected |  | 5.0875 | 141.225 | 0 | 146.3125
|  |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
|  |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
|  |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
|  |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
|  |  | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None |  | 0 | 0 | 0 | 0
| Hours | Minimum | 0 | 0 | 0 | 0 | 10.175 | 10.175 | 10.175 | 0 | 0 | 0 | 10.175 | 10.175 | 10.175 | 10.175 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875 | 5.0875
|  | Expected | 0 | 0 | 0 | 0 | 20.175 | 20.175 | 20.175 | 10.0875 | 10.0875 | 10.0875 | 20.175 | 20.175 | 20.175 | 20.175 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | 30.2625 | Totals | 111.925 | 413.5875 | 15.0875 | 540.6 | Hours
|  | Stretch | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.0875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Hours | Week | 0 | 0 | 0 | 0 | 30.35 | 30.35 | 30.35 | 25.175 | 10.0875 | 10.0875 | 30.35 | 30.35 | 30.35 | 30.35 | 35.35 | 35.35 | 35.35 | 35.35 | 35.35 | 35.35 | 35.35 | 35.35 | Total |  |  | 540.6 |  | Hours
| Total Hours | Sprint | 2018-11-05: 0; 2018-11-19: 0; 2018-12-03: 60.7; 2018-12-17: 55.525; 2018-12-31: 20.175; 2019-01-14: 60.7; 2019-01-28: 60.7; 2019-02-11: 70.7; 2019-02-25: 70.7; 2019-03-11: 70.7; 2019-03-25: 70.7 | Total |  |  | 540.6 |  | Hours
You have | 540.6 | Hours, to spend on your project